## Sheet1
Tasks | w/c 29th Jul | w/c 5th Aug | w/c 12th Aug | w/c 19th Aug | w/c 26th Aug | w/c 2nd Sep | w/c 9th Sep | w/c 16th Sep | w/c 23rd Sep | w/c 30th Sep | w/c 7th Oct
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Problem Identification & Related Work
Baseline Implementation
System Design - Algo., Structures etc.
System Design - Writing
New System Implementation
Experimental Design
Initial Experiments & Setup
Full scale Experiments
Experimetal Analysis & Writing